## RSL
Link Name | WILAYA | Owner | RSL nearend | RSL farend | BO TX feedback | Responsibility | Date | Status | UOP Comment
90001-90002-TFPO1 | TEST-WILAYA-01 | Owner_A | -52.8 | -53.4 | RSL Degraded, link need alignement (planned PO1) | UOP/DTV | 2026-06-20 | Pending | Planned (90001-90002-TFSO1)
90003-90004-TFPO7 | TEST-WILAYA-01 | Owner_A | -42 | -43 | Resolved RSL Requested -39.9 dBm | BO TX | 2026-06-10 | Cleared | Cleared
90005-90006-TFPO17 | TEST-WILAYA-01 | Owner_A | -49.3 | -49.2 | RSL Degraded, link need alignement (planned PO1) | UOP/DTV | 2026-06-20 | Pending | Planned (90005-90006-TFSO1)
90007-90008-TFPO1 | TEST-WILAYA-02 | Owner_A | -51 | -51.4 | Not degraded link RSL Requested -49.98 dBm | BO TX | 2026-05-10 | Cleared
90009-90010-TFPO15 | TEST-WILAYA-02 | Owner_A | -53.6 | -52.6 | RSL Degraded, link need alignement | UOP | 2026-06-20 | Pending | Planned
90011-90012-TFPO15 | TEST-WILAYA-02 | Owner_A | -50 | -50.2 | Cleared RSL actuel -45 dBm, requested -44.8 dBm | BO TX | 2026-05-10 | Cleared | Cleared
90013-90014-TFPO1 | TEST-WILAYA-02 | Owner_A | -46.4 | -47.9 | RSL Degraded, link need alignement | BO TX | 2026-06-20 | Cleared | Cleared
90015-90016-TFPO4 | TEST-WILAYA-02 | Owner_B | -58.1 | -60.9 | Not used Need cleanup & desinstalation | DTV | 2026-09-23 | Pending | Need cleanup & desinstalation
90017-90018-TFPO15 | TEST-WILAYA-02 | Owner_B | -53.5 | -54.5 | RSL Degraded, link need alignement (planned PO1) | UOP/DTV | 2026-06-20 | Pending | Planned PO1
90019-90020-TFPO5 | TEST-WILAYA-02 | Owner_B | -41.8 | -41.6 | Need check ODU SB On 90020, Need alignement | UOP/DTV | 2026-06-20 | Pending | Planned PO1
90021-90022-TFSO1 | TEST-WILAYA-03 | Owner_B | -44.4 | -43.6 | RSL Degraded, channel SB Down (-57dBm) | UOP | 2026-06-20 | Pending
90023-90024-TFPO4 | TEST-WILAYA-03 | Owner_B | -52.1 | -52.7 | RSL Degraded, SD link, RSL Max fadding problem | DTV | 2026-09-23 | Pending | RSL Max fadding problem
90025-90026-TFPO15 | TEST-WILAYA-03 | Owner_B | -45.9 | -51.2 | RSL Degraded, link need alignement requested -33 dBm | UOP | 2026-06-20 | Pending | need swap site MDN To site ATM
90027-90028-TFPO4 | TEST-WILAYA-03 | Owner_B | -70 | -70.2 | RSL Degraded, link need alignement, requested 37 dBm | BO TX | 2026-06-24 | Cleared
90029-90030-TFPO15 | TEST-WILAYA-03 | Owner_C | -75.8 | -74.1 | RSL Degraded, link need alignement (planned PO1) | UOP/DTV | 2026-06-20 | Pending | Obstacle / DR responsibility
90031-90032-TFPO1 | TEST-WILAYA-03 | Owner_C | -48.7 | -52.6 | RSL Degraded, link need alignement | UOP | 2026-06-20 | Pending | Planned
90033-90034-TFPO12 | TEST-WILAYA-03 | Owner_C | -54.2 | -55.3 | RSL Degraded, rerouted to 90106 LOS Validé need installation | UOP | 2026-06-20 | Pending | rerouted to 90106 LOS Validé need installation
90035-90036-TFPO4 | TEST-WILAYA-04 | Owner_C | -45.3 | -47.5 | RSL Degraded, link need alignement | BO TX | 2026-06-20 | Cleared | Cleared
90037-90038-TFPO15 | TEST-WILAYA-04 | Owner_C | -48 | -48.6 | RSL Degraded, link need alignement | BO TX | 2026-06-20 | Cleared | Cleared
90039-90040-TFPO10 | TEST-WILAYA-04 | Owner_C | -49.4 | -50.8 | RSL Degraded, link need alignement | BO TX | 2026-06-20 | Cleared | Cleared
90041-90042-TFPO12 | TEST-WILAYA-04 | Owner_C | -52.6 | -54.8 | RSL Degraded, link need alignement (planned PO1) | UOP/DTV | 2026-06-20 | Pending | Planned PO1
90043-90044-TFPO12 | TEST-WILAYA-04 | Owner_C | -62 | -60.3 | RSL Degraded, link need alignement | BO TX | 2026-07-06 | Cleared | rerouted, Need cleanup & desinstalation
90045-90046-TFSO1 | TEST-WILAYA-04 | Owner_D | -47.8 | -48.3 | RSL Degraded, link need alignement | BO TX | 2026-07-06 | Cleared
90047-90048-TFPO12 | TEST-WILAYA-04 | Owner_D | -46.5 | -50.1 | RSL Degraded, link need alignement | BO TX | 2026-06-20 | Cleared | Cleared
90049-90050-TFPO7 | TEST-WILAYA-05 | Owner_D | -59.4 | -58.3 | RSL Degraded, link need alignement (requested -38 dBm) | UOP | 2026-06-20 | Pending
90051-90052-TFPO12 | TEST-WILAYA-05 | Owner_D | -50.8 | -50.9 | No RSL Problem RSL actuel -46.5 dBm, RSL Requested -48.5 dBm | BO TX | 2026-05-10 | Cleared
90053-90054-TFPO12 | TEST-WILAYA-05 | Owner_D | -53.1 | -52.7 | RSL Degraded, link need alignement (planned PO1) | UOP/DTV | 2026-06-20 | Pending | Planned PO1
90055-90056-TFPO2 | TEST-WILAYA-05 | Owner_D | -57.4 | -59.2 | new link installed 90055-90056-TFSO1 | BO TX | 2026-06-20 | Cleared | Cleared
90057-90058-TFPO12 | TEST-WILAYA-05 | Owner_D | -44.4 | -45.6 | RSL Degraded RSL actuel -43.9 dBm, RSL Requested -33.74 dBm | BO TX | 2026-05-10 | Cleared | Cleared
90059-90060-TFPO7 | TEST-WILAYA-05 | Owner_D | -59.5 | -54.7 | No RSL Problem RSL actuel -36 dBm, RSL Requested -33.84 dBm | BO TX | 2026-05-10 | Cleared
90061-90062-TFPO7 | TEST-WILAYA-06 | Owner_A | -49.2 | -49.5 | No RSL Problem RSL actuel -40 dBm, RSL Requested -38.61 dBm | BO TX | 2026-05-10 | Cleared
90063-90064-TFPO15 | TEST-WILAYA-06 | Owner_A | -52 | -51.3 | No RSL Problem, New link installed | BO TX | 2026-05-10 | Cleared | Cleared
90065-90066-TFPO2 | TEST-WILAYA-06 | Owner_A | -46.1 | -46.5 | RSL Degraded, new link need alignement requested -11 dBm | UOP/DTV | 2026-06-20 | Pending | Planned PO1
90067-90068-TFSO1 | TEST-WILAYA-06 | Owner_A | -46.3 | -46.9 | Not degraded link | BO TX | 2026-05-11 | Cleared
90069-90070-TFSO1 | TEST-WILAYA-06 | Owner_A | -41.3 | -40.9 | Not degraded link | BO TX | 2026-05-11 | Cleared
90071-90072-TFPO17 | TEST-WILAYA-06 | Owner_B | -46.2 | -48 | RSL Degraded, link need alignement | BO TX | 2026-06-20 | Cleared
90073-90074-TFPO12 | TEST-WILAYA-06 | Owner_B | -47.8 | -54 | RSL Degraded, link need alignement (RSL Requested -40 dBm) | BO TX | 2026-08-05 | Cleared | new link 90073-90074-TFSO1
90075-90076-TFPO12 | TEST-WILAYA-01 | Owner_B | -54.3 | -45.2 | Link not used need desinstallation | DTV | 2026-09-23 | Pending | Need cleanup & desinstalation
90077-90078-TFPO12 | TEST-WILAYA-01 | Owner_B | -47.7 | -46.1 | RSL Degraded RSL actuel -46.9 dBm, RSL Requested -41.6 dBm | BO TX | 2026-06-20 | Cleared
90079-90080-TFPO12 | TEST-WILAYA-01 | Owner_B | -47.7 | -49.9 | RSL Degraded, link need alignement (planned PO1) | BO TX | 2026-07-06 | Cleared | New link 90079-90080-TFSO1

## Congestion
Region | WILAYA | Owner | Link name | BO TX feedback | Responsibility | DTV / UOP feedback | Date | Usage | status | Column1
TEST-REGION-01 | TEST-WILAYA-A | Owner_X | 90001-90002-TFPO17 | Swap ok | DTV |  | 2026-10-02 | Usage between 90%-100% | Cleared
TEST-REGION-02 | TEST-WILAYA-B | Owner_X | 90003-90004-TFPO15 | New 2+0 installed, cleared | DTV |  | 2026-10-02 | Usage between 90%-100% | Cleared
TEST-REGION-02 | TEST-WILAYA-B | Owner_X | 90005-90006-TFPO12 | New 4+0 installed, cleared | DTV |  | 2026-10-02 | Usage between 90%-100% | Cleared
TEST-REGION-02 | TEST-WILAYA-B | Owner_X | 90007-90008-TFPO7 | New 4+0 installed, cleared | DTV |  | 2026-10-02 | Usage between 90%-100% | Cleared
TEST-REGION-01 | TEST-WILAYA-C | Owner_Y | 90009-90010-TFPO4 | No alarm actually | DTV |  | 2026-10-02 | Usage between 90%-100% | Cleared
TEST-REGION-03 | TEST-WILAYA-D | Owner_Y | 90011-90012-TFPO10 | No alarm actually | UOP |  | 2026-10-02 | Usage between 90%-100% | Cleared
TEST-REGION-01 | TEST-WILAYA-C | Owner_Y | 90013-90014-TFPO15 | No alarm actually | DTV |  | 2026-10-02 | Usage between 90%-100% | Cleared
TEST-REGION-02 | TEST-WILAYA-B | Owner_Y | 90015-90016-TFPO12 | New 4+0 installed, cleared | DTV |  | 2026-10-02 | Usage between 90%-100% | Cleared
TEST-REGION-01 | TEST-WILAYA-C | Owner_Z | 90017-90018-TFPO10 | No alarm actually | DTV |  | 2026-10-02 | Usage between 90%-100% | Cleared
TEST-REGION-02 | TEST-WILAYA-B | Owner_Z | 90019-90020-TFSO1 | New link installed 4+0, Awaiting swap by HW | DTV |  | 2026-10-02 | Usage between 90%-100% | Cleared
TEST-REGION-01 | TEST-WILAYA-C | Owner_Z | 90021-90022-TFPO15 | Swap ok | DTV |  | 2026-10-02 | Usage between 80%-90% | Cleared
TEST-REGION-02 | TEST-WILAYA-B | Owner_Z | 90023-90024-TFSO1 | New 4+0 installed, cleared | DTV |  | 2026-10-02 | Usage between 80%-90% | Cleared
TEST-REGION-03 | TEST-WILAYA-D | Owner_X | 90025-90026-TFPO17 | No alarm actually | UOP |  | 2026-10-02 | Usage between 80%-90% | Cleared
TEST-REGION-03 | TEST-WILAYA-D | Owner_X | 90027-90028-TFSO1 | No alarm actually | UOP |  | 2026-10-02 | Usage between 80%-90% | Cleared
TEST-REGION-01 | TEST-WILAYA-C | Owner_X | 90029-90030-TFPO15 | No alarm actually | UOP |  | 2026-10-02 | Usage between 80%-90% | Cleared
TEST-REGION-01 | TEST-WILAYA-C | Owner_X | 90031-90032-TFPO5 | No alarm actually | DTV |  | 2026-10-02 | Usage between 80%-90% | Cleared
TEST-REGION-01 | TEST-WILAYA-C | Owner_X | 90033-90034-TFPO12 | No alarm actually | DTV |  | 2026-10-02 | Usage between 80%-90% | Cleared
TEST-REGION-02 | TEST-WILAYA-B | Owner_Y | 90035-90036-TFSO1 | Link installed 1+1 HSB, need upgrade | DTV |  | 2026-10-02 | Usage between 80%-90% | Cleared
TEST-REGION-01 | TEST-WILAYA-C | Owner_Y | 90037-90038-TFPO15 | Awaiting new link installation | DTV |  | 2026-10-02 | Usage between 80%-90% | Cleared
TEST-REGION-02 | TEST-WILAYA-B | Owner_Y | 90039-90040-TFPO12 | Link installed 6+0, need DTV solution | DTV |  | 2026-10-02 | Usage between 80%-90% | Cleared
TEST-REGION-03 | TEST-WILAYA-D | Owner_Y | 90041-90042-TFPO10 | link 4+0, need HW upgrade | DTV | No action | 2026-10-02 | Usage between 90%-100% | Pending
TEST-REGION-03 | TEST-WILAYA-D | Owner_Z | 90043-90044-TFPO12 | New link installed 8+0, Awaiting swap by HW | DTV | 90043-90044-TFSO1 implementation ongoing | 2026-09-23 | Usage between 90%-100% | Pending
TEST-REGION-02 | TEST-WILAYA-B | Owner_Z | 90045-90046-TFPO4 | Rsl degraded -63dBm in 90045 side & -62dBm in 90046 side | UOP |  | 2026-10-02 | Usage between 90%-100% | Pending
TEST-REGION-01 | TEST-WILAYA-C | Owner_Z | 90047-90048-TFPO12 | Awaiting new Eband planned in PO1, escalated to DTV | DTV |  | 2026-07-15 | Usage between 90%-100% | Pending
TEST-REGION-02 | TEST-WILAYA-B | Owner_X | 90049-90050-TFPO7 | Channel down, escalated to UOP | UOP |  | 2026-10-02 | Usage between 90%-100% | Pending
TEST-REGION-04 | TEST-WILAYA-E | Owner_X | 90051-90052-TFPO5 | Congested due the link 1+1 RSL degraded to -50.4 dbm need realignement | DTV | lien sécurisation / BO tx confirm | 2026-04-28 | Usage between 90%-100% | Cleared
TEST-REGION-04 | TEST-WILAYA-E | Owner_X | 90053-90054-TFSO1 | after intervention UOP team RSL decrease to -38 dbm and congestion decrease to 50% | UOP | 0 | 2026-04-28 | Usage between 80%-90% | Cleared
TEST-REGION-04 | TEST-WILAYA-F | Owner_Y | 90055-90056-TFPO12 | congestion due the link 4+0 SW/BW 28Mhz in MAX capacity 2048QAM we need DTV to SW upgrade BW to 56 QAM | DTV | 0 | 2026-04-28 | Usage between 90%-100% | Cleared
TEST-REGION-04 | TEST-WILAYA-F | Owner_Y | 90057-90058-TFSO1 | congestion due the link RSL degraded | UOP | 0 | 2026-04-28 | Usage between 90%-100% | Cleared
TEST-REGION-04 | TEST-WILAYA-E | Owner_Y | 90059-90060-TFPO1 | PLA member down because of 10G cascade between the E-BAND and the K-BAND RTN is down | UOP |  | 2026-04-28 | Usage between 80%-90% | Pending

## Sheet1
Row Labels | Pending | Grand Total
DTV | 3 | 3
Usage between 90%-100% | 3 | 3
UOP | 3 | 3
Usage between 80%-90% | 1 | 1
Usage between 90%-100% | 2 | 2
Grand Total | 6 | 6